## Sheet1
Risk Matrices
| Negligible | Minor | Major | Hazardous | Catastrophic
Very Unlikely | Low | Low | Low medium | Medium | Medium
Unlikely | Low | Low Medium | Low medium | Medium | Medium HIgh
Moderate | Low | Low Medium | Medium | Medium High | Medium HIgh
Likely | Low | Low medium | Medium | Medium high | High
Very Likely | Low medium | Medium | Medium high | High | High
Risk | Statement | Response | Objective | Likelihood | Impact | Risk Level
RSI | Possibility of injuring wrists | Ensuring adequate movement between coding sessions | To make sure the no injury is sustained during working | Very Unlikely | Minor | Low
Losing my Work | Losing all produced work, would lead to a halt in the progress of work | Ensuring that work is always being saved | My pushing to the github regularly after work is completed | Very Unlikely | Catastrophic | High
Injury | Involvement in activity could lead to injury during project and become incapable of finishing project | Ensure i exercise responsibly and rest well. | be cautious when exercising to prevent injury and eat a balanced diet to decrease recovery time if injured. | Moderate | Major | Medium
Computer Malfunctioning | Loss of Computer services | Making sure that all the softwares are updated | Monitoring computer security and health by regularly updating it. | Very Unlikely | Hazardous | Medium
GitHub Servers being down | I would then be unable to access the remote work to enhance development | Ensure my I regularly check GitHub status. | ensure my remote repository is up-to date with my GitHub repository at all times. | Very Unlikely | Catastrophic | Medium
Mentor is not present | Due to any possible reasons | Look for solutions in alternative places or contact other team memebers and see if they have a possible solution and problems that I may fafce | use resources on QA Community or other places such as Stack Overflow | Moderate | Minor | Low Medium
Bad Internet / No Internet | Loss of internet preventing access to GitHub And not being able to reach my cohort on Teams | Ensuring that I have a stable internet connection | ensure that the Wi-Fi connection is stable alternative use my hotspot if internet goes down. | Unlikely | Hazardous | Medium
Problems in Merging between two branches | Could happen due to incorrect branching workflow Which will lead to merge conflicts during feature merging. | Ensuring that all work is being saved in the correct branch | keep track of the feature-branch workflow and ensure to branch off develop branch to follow branching best practises and that the branches have a shared history. | Moderate | Minor | Low Medium